## Invoice Due Dates
PAY APPLICATION/INVOICE DUE DATES 2025
Invoices are approved during the Monthly Board Meetings.
Work Completed During the Month of: | Contractor Uploads Formal Pay Application in e-Builder1 | CM Approves Pay Application in eBuilder | PM Approval in e-Builder | Manager and Director Approval in e-Builder | Accounting Due Date | Change Order Exhibits Due2 (by Weds the week prior to Board Meeting) | Board Meeting Date
2024-12-01 | 2024-12-31 | 2025-01-01 | 2025-01-03 | 2025-01-07 | 2025-01-09 | 2025-01-15 | 2025-01-23
2025-01-01 | 2025-02-04 | 2025-02-05 | 2025-02-07 | 2025-02-11 | 2025-02-13 | 2025-02-19 | 2025-02-27
2025-02-01 | 2025-03-04 | 2025-03-05 | 2025-03-07 | 2025-03-11 | 2025-03-13 | 2025-03-19 | 2025-03-27
2025-03-01 | 2025-04-01 | 2025-04-02 | 2025-04-04 | 2025-04-08 | 2025-04-10 | 2025-04-16 | 2025-04-24
2025-04-01 | 2025-04-22 | 2025-04-23 | 2025-04-25 | 2025-04-29 | 2025-05-01 | 2025-05-07 | 2025-05-15
2025-05-01 | 2025-06-03 | 2025-06-04 | 2025-06-06 | 2025-06-10 | 2025-06-12 | 2025-06-18 | 2025-06-26
2025-06-01 | 2025-07-01 | 2025-07-02 | 2025-07-04 | 2025-07-08 | 2025-07-10 | 2025-07-16 | 2025-07-24
No Board Meeting in August
2025-08-01 | 2025-09-02 | 2025-09-03 | 2025-09-05 | 2025-09-09 | 2025-09-11 | 2025-09-17 | 2025-09-25
2025-09-01 | 2025-09-30 | 2025-10-01 | 2025-10-03 | 2025-10-07 | 2025-10-09 | 2025-10-15 | 2025-10-23
2025-10-01 | 2025-10-28 | 2025-10-29 | 2025-10-31 | 2025-11-04 | 2025-11-06 | 2025-11-12 | 2025-11-20
2025-11-01 | 2025-11-17 | 2025-11-18 | 2025-11-20 | 2025-11-24 | 2025-11-26 | 2025-12-03 | 2025-12-11
Note 1: Contractor must upload APPROVED (pencil copy) pay application approximately 3 weeks prior to Board Meetings.
Note 2: Change Orders (Exhibits) that meet the deadline and are approved at the Board Meeting can then be included on the following month's Pay Application.
Indicates hard deadlines - if these deadlines are missed, the invoice will have to wait until the following month/meeting
Notes:
We pay our Invoices in 60 days. Approval processes take time. If your invoice is approved before the Accounting Due Date, it will make the Board list for payment.
Invoices under $10,900.00 are paid upon receipt of approval.
Invoices over $10,900.00 are paid after Board approval.
Dates are subject to change. They are based on the Board Meeting Dates that are not approved until the December Board meeting.